## Sheet1
Kode | User Stories | Acceptance Criteria | Backlogs | SP
MA-04 | As a user, I want to register or login with my existing account so that I can access Monica | User should be able to see app logo | Image: Logo | 1
|  | User should be able to click login button | Button: Login | 1
|  | User should be able to click register button | Button: Register | 1
|  | User should be able to see landing page | Activity: landingPage | 1
MA-05 | As a user, I want to login with my email and password so that I can authenticate as me | User should be able to input e-mail | Input text: Email | 1
|  | User should be able to input password | Input text: Password | 1
|  | User should be able to click login button | Button: Login | 1
|  | User should be able to see login page | Activity: Login | 4
MA-06 | As a user, I want to register a new account so that I can use Monica | User should be able to input e-mail | Input text: Email | 1
|  | User should be able to input username | Input text: Username | 1
|  | User should be able to input password | Input text: Password | 1
|  | User should be able to input password again | Input text: Re-enter Password | 1
|  | User should be able to click register button | Button: Register | 1
|  | User should be able to see register page | Activity: Register | 4
MA-07 | As a user, I want to see agendas so that I can remember things to do or meetings to go | User should be able to see agendas in calendar | Calendar: With tasks, items, and meetings | 8
|  | User should be able to see home page | Activity: homePage | 4
MA-08 | As a user, I want to see all ongoing committees so that I can see the committee activities in communications and databases | User should be able to see committee list in drawer | Drawer: To see committee list | 4
|  | User should be able to see committee list | ListView: Committee list | 4
|  | User should be able to see committee’s logo | Image: Committee’s logo | 1
|  | User should be able to see committee’s name | Text: Committee’s name | 1
|  | User should be able to navigate to each committee page | Link: To navigate to each committee page | 3
MA-09 | As a project officer, I want to create a committee so that I can invite all committee members and track committee activities using Monica’s features | User should be able to input committee name | Input text: Committee name | 1
|  | User should be able to input committee description | Input text: Committee description | 1
|  | User should be able to upload committee’s logo | Button: Upload committee’s logo | 3
|  | User should be able to input division name | Input text: Division name | 1
|  | User should be able to add division | Button: Add division | 3
|  | User should be able to see generated invitation link | Text: Generated invitation code | 4
|  | User should be able to create committee | Button: Create committee | 4
|  | User should be able to see create committee page | Activity: createCommittee | 1
MA-10 | As a head of division, I want to invite my division’s members so that I can communicate with all of my division’s members | User should be able to add member by e-mail/username | Input text: Add member by e-mail/username | 12
|  | User should be able to add all members | Button: Add all | 7
MA-11 | As a user, I want to see to do list so that I can add or tick my to do tasks | User should be able to input text in new task | Input text: Add new task | 1
|  | User should be able to click add button | Button: Add | 1
|  | User should be able to click delete button | Button: Delete | 1
|  | User should be able to see to do list page | ListView: To do list | 1
|  | User should be able to click text in list page, which make the text strikethrough | Text: To do task title, if checked, the text will have strikethrough | 3
|  | User should be able to click tick task button | Button: Tick task to complete task | 3
|  | User should be able to see toDoList page | Activity: toDoList | 3
MA-12 | As a user especially logistics division, I want to see item list so that I can add or tick items that should be prepared | User should be able to input text in new item | Input text: Add new item | 1
|  | User should be able to click add button | Button: Add | 1
|  | User should be able to click delete button | Button: Delete | 1
|  | User should be able to see item list | ListView: Item list | 1
|  | User should be able to click text in item list which make the item text become strikethrough | Text: Item task title, if checked, the text will have strikethrough | 3
|  | User should be able to click tick item button | Button: Tick item to complete preparing item | 3
|  | User should be able to see itemList page | Activity: itemList | 3
MA-13 | As a user, I want to see files manager so that I can add, edit, or delete committee files | User should be able to input text in search file | Input text: Search file | 1
|  | User should be able to click search button | Button: Search | 3
|  | User should be able to see folder list | ListView: Folder list | 2
|  | User should be able to see file list | ListView: File list | 2
|  | User should be able to click a folder (folder button) | ImageButton: Folder | 1
|  | User should be able to click a file (file button) | ImageButton: File | 1
|  | User should be able to click add folder button | ImageButton: Add Folder | 2
|  | User should be able to click add file button | ImageButton: Add File | 2
|  | User should be able to see fileManager page | Activity: fileManager | 8
Total Story Points |  |  |  | 130