## Sheet1
Story | Backlog | SP | Assignee | Time to finish (person/hour)
|  |  |  | Sprint 1 | [7 empty] | Sprint 2 | [7 empty] | Sprint 3 | [7 empty] | Sprint 4 | [7 empty] | Sprint 5 | [7 empty] | Sprint 6 | [7 empty] | Sprint 7 | [7 empty] | Sprint 8 | [7 empty] | Sprint 9 | [7 empty] | Sprint 10
|  |  |  | Estimate | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | Estimate | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | Estimate | 2019-04-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | Estimate | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | Estimate | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2019-05-09 | Estimate | 2019-05-10 | 2019-05-11 | 2019-05-12 | 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | Estimate | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | Estimate | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | Estimate | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | Estimate | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13
Expected execution per week |  |  |  | 13 | 1.8571 | 1.8571 | 1.8571 | 1.8571 | 1.8571 | 1.8571 | 1.8571 | 16 | 2.2857 | 2.2857 | 2.2857 | 2.2857 | 2.2857 | 2.2857 | 2.2857 | 19 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 24 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 26 | 3.7143 | 3.7143 | 3.7143 | 3.7143 | 3.7143 | 3.7143 | 3.7143 | 19 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 2.7143 | 27 | 3.8571 | 3.8571 | 3.8571 | 3.8571 | 3.8571 | 3.8571 | 3.8571 | 30 | 4.2857 | 4.2857 | 4.2857 | 4.2857 | 4.2857 | 4.2857 | 4.2857 | 52 | 7.4286 | 7.4286 | 7.4286 | 7.4286 | 7.4286 | 7.4286 | 7.4286 | 20 | 2.8571 | 2.8571 | 2.8571 | 2.8571 | 2.8571 | 2.8571 | 2.8571
Real execution per week |  |  |  | 10 | 2 | 0 | 3 | 1 | 1 | 1 | 2 | 10 | 2 | 0 | 8 | 0 | 0 | 0 | 0 | 13 | 1 | 3 | 2 | 4 | 1 | 1 | 1 | 10 | 1 | 3 | 0 | 0 | 2 | 4 | 0 | 11 | 1 | 2 | 3 | 4 | 1 | 0 | 0 | 8 | 0 | 2 | 4 | 1 | 1 | 0 | 0 | 16 | 2 | 3 | 1 | 5 | 2 | 2 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | 9 | 6 | 5 | 8 | 2 | 1 | 20 | 0 | 0 | 2 | 2 | 3 | 13 | 0
As a user, I want to register or login with my existing account so that I can access Monica | Image: Logo | 1 | Patricia | [42 empty] | 1
| Button: Login | 1 | Patricia | [43 empty] | 1
| Button: Register | 1 | Patricia | [43 empty] | 1
| Activity: landingPage | 1 | Patricia | [43 empty] | 1
As a user, I want to login with my email and password so that I can authenticate as me | Input text: Email | 1 | Patricia | [50 empty] | 1
| Input text: Password | 1 | Patricia | [50 empty] | 1
| Button: Login | 1 | Patricia | [50 empty] | 1
| Activity: Login | 4 | Patricia | [49 empty] | 2 |  | 1 | 1
As a user, I want to register a new account so that I can use Monica | Input text: Email | 1 | Patricia | [52 empty] | 1
| Input text: Username | 1 | Patricia | [52 empty] | 1
| Input text: Password | 1 | Patricia | [52 empty] | 1
| Input text: Re-enter Password | 1 | Patricia | [52 empty] | 1
| Button: Register | 1 | Patricia | [53 empty] | 1
| Activity: Register | 4 | Patricia | [53 empty] | 1 | 2 | 1
As a user, I want to see agendas so that I can remember things to do or meetings to go | Calendar: With tasks, items, and meetings | 8 | Raihan | [36 empty] | 3 | 1 |  |  |  |  | 1 | 1 | 1 | 1
| Activity: homePage | 4 | Raihan | [33 empty] | 1 | 2 | 1
As a user, I want to see all ongoing committees so that I can see the committee activities in communications and databases | Drawer: To see committee list | 4 | Patricia | [17 empty] | 1 | 2 | 1
| ListView: Committee list | 4 | Patricia | [18 empty] | 1 | 1 | 2
| Image: Committee’s logo | 1 | Patricia | [20 empty] | 1
| Text: Committee’s name | 1 | Patricia | [20 empty] | 1
| Link: To navigate to each committee page | 3 | Patricia | [21 empty] | 1 | 1 | 1
As a project officer, I want to create a committee so that I can invite all committee members and track committee activities using Monica’s features | Input text: Committee name | 1 | Rifqy | [26 empty] | 1
| Input text: Committee description | 1 | Rifqy | [26 empty] | 1
| Button: Upload committee’s logo | 3 | Rifqy | [57 empty] | 1 | [8 empty] | 1 | 1 | 1
| Input text: Division name | 1 | Rifqy | [26 empty] | 1
| Button: Add division | 3 | Rifqy | [35 empty] | 2 | 1
| Text: Generated invitation code | 4 | Rifqy | [57 empty] | 1 | [8 empty] | 1 | 2 | 1
| Button: Create committee | 4 | Rifqy | [57 empty] | 1 | [8 empty] | 1 |  |  | 1 | 1
| Activity: createCommittee | 1 | Rifqy | [25 empty] | 1
As a head of division, I want to invite my division’s members so that I can communicate with all of my division’s members | Input text: Add member by e-mail/username | 12 | Rifqy | [66 empty] | 2 | [8 empty] | 1 | 1 | 1 | 7
| Button: Add all | 7 | Rifqy | [77 empty] | 1 | 6
As a user, I want to see to do list so that I can add or tick my to do tasks | Input text: Add new task | 1 | Raihan |  |  |  | 1
| Button: Add | 1 | Raihan |  |  |  | 1
| Button: Delete | 1 | Raihan |  |  |  | 1
| ListView: To do list | 1 | Raihan |  | 1
| Text: To do task title, if checked, the text will have strikethrough | 3 | Raihan | [29 empty] | 2 | 1
| Button: Tick task to complete task | 3 | Raihan |  |  |  |  | 1 | 1 |  | 1
| Activity: toDoList | 3 | Raihan |  | 1 |  |  |  |  | 1 | 1
As a user especially logistics division, I want to see item list so that I can add or tick items that should be prepared | Input text: Add new item | 1 | Raihan | [11 empty] | 1
| Button: Add | 1 | Raihan | [11 empty] | 1
| Button: Delete | 1 | Raihan | [11 empty] | 1
| ListView: Item list | 1 | Raihan | [9 empty] | 1
| Text: Item task title, if checked, the text will have strikethrough | 3 | Raihan | [30 empty] | 3
| Button: Tick item to complete preparing item | 3 | Raihan | [11 empty] | 3
| Activity: itemList | 3 | Raihan | [9 empty] | 1 |  | 2
As a user, I want to see files manager so that I can add, edit, or delete committee files | Input text: Search file | 1 | Raihan | [71 empty] | 1
| Button: Search | 3 | Raihan | [75 empty] | 1 | 1 | 1
| ListView: Folder list | 2 | Raihan | [67 empty] | 1 | 1
| ListView: File list | 2 | Raihan | [67 empty] | 1 | 1
| ImageButton: Folder | 1 | Raihan | [69 empty] | 1
| ImageButton: File | 1 | Raihan | [69 empty] | 1
| ImageButton: Add Folder | 2 | Raihan | [66 empty] | 1 |  |  | 1
| ImageButton: Add File | 2 | Raihan | [66 empty] | 1 |  |  | 1
| Activity: fileManager | 8 | Raihan | [66 empty] | 2 | 1 | 1 | 3 | 1
Catatan:
[6 empty] | = | task yang baru ditambah
[6 empty] | = | task yang belum selesai
[6 empty] | = | task yang sudah selesai